## Functional_Test_Cases
Functional Testing
Test Case ID | Test Scenario | Requirement ID | Test Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Remarks | Tested By | Approved By | Approval Date
FT001 | User Login | REQ-001 | Verify registered user can log in successfully | User registered with valid credentials | 1. Open login page 2. Enter valid username & password 3. Click login | Valid username & password | User dashboard loads successfully | User dashboard loaded successfully | Pass | High |  | Vaishnavi | Kruthana | 2025-03-15
FT002 | Fund Transfer | REQ-002 | Verify user can transfer funds to another account | User logged in with sufficient balance | 1. Login 2. Go to transfer 3. Enter recipient & amount 4. Confirm | Recipient ID, amount | Funds transferred, balance updated | Funds transferred and balance updated | Pass | High |  | Vaishnavi | Kruthana | 2025-03-15
FT003 | View Account Balance | REQ-003 | Verify user can view current account balance | User logged in | 1. Login 2. Navigate to balance page | None | Correct account balance displayed | Account balance displayed correctly | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
FT004 | Password Reset | REQ-004 | Verify password reset via email | Registered email available | 1. Click “Forgot Password” 2. Enter registered email 3. Follow link | Registered email | Password reset email sent & password updated | Reset email received, password reset successful | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
FT005 | Logout | REQ-005 | Verify user can logout successfully | User logged in | 1. Click logout button | None | User logged out, redirected to login page | User logged out and redirected | Pass | Low |  | Vaishnavi | Kruthana | 2025-03-15
FT006 | Add New Beneficiary | REQ-006 | Verify user can add a new beneficiary | User logged in | 1. Navigate to beneficiary section 2. Add new beneficiary details | Beneficiary info | New beneficiary added successfully | Beneficiary added successfully | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
FT007 | View Transaction History | REQ-007 | Verify user can view transaction history | User logged in | 1. Login 2. Navigate to transaction history | None | Transaction list displayed | Transactions displayed correctly | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
FT008 | Update Profile Information | REQ-008 | Verify user can update personal profile | User logged in | 1. Navigate to profile section 2. Update info 3. Save changes | New profile info | Profile updated successfully | Profile updated successfully | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
FT009 | Change Password | REQ-009 | Verify user can change password | User logged in | 1. Go to settings 2. Enter old & new passwords 3. Submit | Old and new passwords | Password updated successfully | Password changed successfully | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
FT010 | Check Notifications | REQ-010 | Verify user receives notifications | User logged in | 1. Login 2. Check notification panel | None | Notifications displayed | Notifications shown correctly | Pass | Low |  | Vaishnavi | Kruthana | 2025-03-15
FT011 | Add Funds to Account | REQ-011 | Verify user can add funds via payment gateway | User logged in | 1. Login 2. Go to add funds 3. Select payment method 4. Confirm | Payment info | Funds added and balance updated | Funds added successfully | Pass | High |  | Vaishnavi | Kruthana | 2025-03-15
FT012 | Schedule Payments | REQ-012 | Verify user can schedule future payments | User logged in | 1. Login 2. Go to payments 3. Schedule payment with date | Recipient & date | Payment scheduled | Payment scheduled successfully | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
FT013 | Receive Payments | REQ-013 | Verify user receives payments successfully | User logged in | 1. Send payment to user 2. Check account | Payment from another user | Payment received and balance updated | Payment received successfully | Pass | High |  | Vaishnavi | Kruthana | 2025-03-15
FT014 | Block Account | REQ-014 | Verify user can block account temporarily | User logged in | 1. Go to settings 2. Select block account 3. Confirm | None | Account blocked temporarily | Account blocked successfully | Pass | High |  | Vaishnavi | Kruthana | 2025-03-15
FT015 | Unblock Account | REQ-015 | Verify user can unblock account | Account is blocked | 1. Go to settings 2. Select unblock 3. Confirm | None | Account unblocked | Account unblocked successfully | Pass | High |  | Vaishnavi | Kruthana | 2025-03-15
FT016 | View Beneficiary Details | REQ-016 | Verify user can view details of added beneficiaries | User logged in with beneficiaries | 1. Go to beneficiary list 2. Select beneficiary | None | Beneficiary details displayed | Beneficiary details displayed | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
FT017 | Delete Beneficiary | REQ-017 | Verify user can delete a beneficiary | User logged in with beneficiaries | 1. Go to beneficiary list 2. Select delete | None | Beneficiary deleted | Beneficiary deleted successfully | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
FT018 | Generate Account Statement | REQ-018 | Verify user can generate account statement | User logged in | 1. Go to statements 2. Select period 3. Generate statement | Date range | Statement generated successfully | Statement generated successfully | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
FT019 | Export Transaction History | REQ-019 | Verify user can export transaction history | User logged in | 1. Go to transactions 2. Click export | None | Export file downloaded | Export file downloaded successfully | Pass | Low |  | Vaishnavi | Kruthana | 2025-03-15
FT020 | Multi-language Support | REQ-020 | Verify app supports multiple languages | App installed | 1. Change language settings 2. Navigate app | Language selection | App displays in selected language | App displayed correctly in selected language | Pass | Low |  | Vaishnavi | Kruthana | 2025-03-15
FT021 | Session Timeout | REQ-021 | Verify session times out after inactivity | User logged in | 1. Login 2. Remain inactive for timeout period | None | User session ends, redirected to login page | Session timed out and user logged out | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
FT022 | Two-Factor Authentication | REQ-022 | Verify two-factor authentication during login | User enabled 2FA | 1. Login 2. Enter username/password 3. Enter 2FA code | Valid credentials & 2FA code | Login successful after 2FA validation | Login successful after 2FA | Pass | High |  | Vaishnavi | Kruthana | 2025-03-15
FT023 | Notification Preferences | REQ-023 | Verify user can update notification preferences | User logged in | 1. Go to settings 2. Update notification settings 3. Save | Preference settings | Preferences saved | Preferences saved successfully | Pass | Low |  | Vaishnavi | Kruthana | 2025-03-15
FT024 | Add Linked Bank Account | REQ-024 | Verify user can link external bank account | User logged in | 1. Go to bank accounts 2. Add new account 3. Submit | Bank account details | Bank account linked successfully | Bank account linked successfully | Pass | High |  | Vaishnavi | Kruthana | 2025-03-15
FT025 | Delete Linked Bank Account | REQ-025 | Verify user can delete linked bank account | User logged in with linked accounts | 1. Go to linked accounts 2. Select delete 3. Confirm | None | Linked bank account deleted | Linked bank account deleted successfully | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15

## Integration_Test_Cases
Integration Testing
Test Case ID+A33:A57 | Test Scenario | Requirement ID | Test Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Remarks | Tested By | Approved By | Approval Date
IT001 | Login - Database Integration | REQ-101 | Verify login module integration with user database | User registered | 1. Enter login credentials 2. System checks database | Valid username & password | User authenticated via database | User authenticated successfully | Pass | High |  | Vaishnavi | Kruthana | 2025-03-15
IT002 | Fund Transfer - Payment Gateway | REQ-102 | Verify fund transfer integrates with external payment gateway | User logged in, payment gateway active | 1. Initiate transfer 2. Payment gateway processes transaction | Recipient & amount | Funds transferred & payment gateway confirms payment | Transfer processed successfully | Pass | High |  | Vaishnavi | Kruthana | 2025-03-15
IT003 | Notification System Integration | REQ-103 | Verify notification service sends alerts on transactions | User performs transaction | 1. Perform transaction 2. System sends notification | Transaction data | Notification sent successfully | Notification sent successfully | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
IT004 | Account Balance - Database Sync | REQ-104 | Verify balance update synced correctly with database | User performs transaction | 1. Complete transaction 2. Check database balance update | Transaction details | Database reflects new balance | Database balance updated | Pass | High |  | Vaishnavi | Kruthana | 2025-03-15
IT005 | User Profile - CRM Integration | REQ-105 | Verify profile updates synced with CRM system | User updates profile | 1. Update profile 2. Sync with CRM | Updated profile data | CRM updated with user profile changes | CRM updated successfully | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
IT006 | Two-Factor Authentication - SMS | REQ-106 | Verify 2FA SMS service integration | User enabled 2FA | 1. Login 2. Receive SMS code 3. Enter code | Valid credentials & SMS code | SMS received and verified | SMS received and verified | Pass | High |  | Vaishnavi | Kruthana | 2025-03-15
IT007 | Transaction History - Reporting | REQ-107 | Verify transaction data correctly passed to reporting module | User views transactions | 1. View transactions 2. Generate report | Transaction data | Report generated with accurate data | Report generated correctly | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
IT008 | Payment Gateway - Fraud Check | REQ-108 | Verify fraud detection system integrated with payments | Payment gateway active | 1. Perform payment 2. Fraud system scans transaction | Transaction details | Fraud check completed | Fraud check passed | Pass | High |  | Vaishnavi | Kruthana | 2025-03-15
IT009 | Account Locking - Security Module | REQ-109 | Verify security module locks account after failed attempts | User attempts multiple failed logins | 1. Enter wrong passwords repeatedly 2. Account locks | Invalid login attempts | Account locked after threshold | Account locked successfully | Pass | High |  | Vaishnavi | Kruthana | 2025-03-15
IT010 | Payment Gateway Refund Process | REQ-110 | Verify refund process integration with payment gateway | Payment failed | 1. Initiate refund 2. Check gateway response | Transaction ID | Refund processed and gateway confirms | Refund processed successfully | Pass | High |  | Vaishnavi | Kruthana | 2025-03-15
IT011 | Logout - Session Termination | REQ-111 | Verify logout triggers session termination in backend | User logged in | 1. Logout 2. Check session status | None | Session terminated in DB | Session terminated and user logged out | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
IT012 | Scheduled Payments - DB & UI | REQ-112 | Verify scheduled payments sync between UI and DB | User scheduled payment | 1. Schedule payment 2. Check DB and UI | Payment details | Scheduled payment appears in DB and UI | Scheduled payment synced correctly | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
IT013 | Notification Service & DB Sync | REQ-113 | Verify notifications stored in DB and sent to user | User logged in | 1. Trigger notification 2. Check DB and user device | Notification trigger data | Notification logged and sent | Notification logged and sent | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
IT014 | Export Statement - File System | REQ-114 | Verify export file generated is saved and downloadable | User logged in | 1. Export statement 2. Verify file created | Date range | File generated and available for download | File generated and downloaded successfully | Pass | Low |  | Vaishnavi | Kruthana | 2025-03-15
IT015 | Update Profile - DB Commit | REQ-115 | Verify profile updates saved in database | User logged in | 1. Update profile 2. Save changes 3. Check DB | New profile data | Profile info updated in DB | Profile updated successfully | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
IT016 | Delete Beneficiary - DB Update | REQ-116 | Verify deleting beneficiary removes record from DB | User logged in with beneficiary | 1. Delete beneficiary 2. Verify DB | Beneficiary ID | Beneficiary record deleted in DB | Beneficiary deleted successfully | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
IT017 | Add Funds - Payment Gateway | REQ-117 | Verify add funds transaction integrates with payment gateway | User logged in | 1. Add funds 2. Payment gateway confirms payment | Payment details | Funds added, payment successful | Funds added successfully | Pass | High |  | Vaishnavi | Kruthana | 2025-03-15
IT018 | Block Account - Backend API | REQ-118 | Verify block account API updates account status correctly | User logged in | 1. Block account 2. Check account status via API | Account ID | Account status updated to blocked | Account blocked successfully | Pass | High |  | Vaishnavi | Kruthana | 2025-03-15
IT019 | Unblock Account - Backend API | REQ-119 | Verify unblock account API updates account status correctly | Account blocked | 1. Unblock account 2. Check account status via API | Account ID | Account status updated to active | Account unblocked successfully | Pass | High |  | Vaishnavi | Kruthana | 2025-03-15
IT020 | Linked Bank Account Add - API | REQ-120 | Verify API adds linked bank account correctly | User logged in | 1. Add bank account via API 2. Check DB | Bank account data | Bank account linked and stored | Bank account linked successfully | Pass | High |  | Vaishnavi | Kruthana | 2025-03-15
IT021 | Linked Bank Account Delete API | REQ-121 | Verify API deletes linked bank account | User logged in with linked account | 1. Delete bank account via API 2. Verify DB | Bank account ID | Bank account deleted | Bank account deleted successfully | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
IT022 | Export Data - File System Sync | REQ-122 | Verify export files saved correctly to filesystem | User logged in | 1. Export data 2. Check filesystem | Export parameters | File saved correctly | File saved successfully | Pass | Low |  | Vaishnavi | Kruthana | 2025-03-15
IT023 | Session Timeout - Backend Sync | REQ-123 | Verify backend invalidates session after timeout | User logged in | 1. Remain inactive 2. Check session status | None | Session invalidated | Session invalidated correctly | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-15
IT024 | Payment Status Update | REQ-124 | Verify payment status updates reflect across all systems | Payment initiated | 1. Make payment 2. Verify status in UI and DB | Payment ID | Status updated consistently | Status updated correctly | Pass | High |  | Vaishnavi | Kruthana | 2025-03-15

## System_Test_CAse
System Testing
Test Case ID | Test Scenario | Requirement ID | Test Description | Preconditions | Test Steps | Test Data | Expected Result | Actual Result | Status | Severity | Remarks | Tested By | Approved By | Approval Date
ST001 | Full Application Login | REQ-201 | Verify user can login with valid credentials | App deployed | 1. Open app 2. Enter valid credentials 3. Click login | Valid username/password | User logged in successfully | Login successful | Pass | High |  | Vaishnavi | Kruthana | 2025-03-16
ST002 | User Registration Flow | REQ-202 | Verify new user registration completes end-to-end | App deployed | 1. Open registration 2. Fill form 3. Submit | Valid registration data | User registered and confirmation received | Registration successful | Pass | High |  | Vaishnavi | Kruthana | 2025-03-16
ST003 | Password Reset End-to-End | REQ-203 | Verify password reset works across UI, backend, email | Registered user exists | 1. Request reset 2. Receive email 3. Reset password | Registered email | Password reset successfully | Password reset successful | Pass | High |  | Vaishnavi | Kruthana | 2025-03-16
ST004 | Fund Transfer | REQ-204 | Verify user can transfer funds between accounts | User logged in | 1. Enter transfer details 2. Submit | Valid account details | Funds transferred successfully | Transfer completed | Pass | High |  | Vaishnavi | Kruthana | 2025-03-16
ST005 | View Account Balance | REQ-205 | Verify balance shown matches backend data | User logged in | 1. Navigate to balance page | None | Balance matches database value | Balance shown correctly | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-16
ST006 | Add Beneficiary | REQ-206 | Verify adding beneficiary flows end-to-end | User logged in | 1. Add beneficiary 2. Confirm added | Beneficiary data | Beneficiary added and visible | Beneficiary added successfully | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-16
ST007 | Logout Functionality | REQ-207 | Verify logout ends session and redirects user | User logged in | 1. Click logout | None | User logged out and session terminated | Logout successful | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-16
ST008 | Notification Receive and View | REQ-208 | Verify notifications received and viewed correctly | User logged in | 1. Trigger notification 2. View notification | Notification trigger | Notification received and marked read | Notification handled correctly | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-16
ST009 | Export Statement File | REQ-209 | Verify exporting account statement generates correct file | User logged in | 1. Export statement for date range | Date range | Correct file generated | File generated and downloadable | Pass | Low |  | Vaishnavi | Kruthana | 2025-03-16
ST010 | Session Timeout | REQ-210 | Verify session times out after inactivity | User logged in | 1. Remain inactive for timeout duration | None | User session expires and user logged out | Session timeout working | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-16
ST011 | Multi-language Support | REQ-211 | Verify app switches languages correctly | App supports multi-language | 1. Change language 2. Verify UI text | Language selection | UI text displays in selected language | Language switch successful | Pass | Low |  | Vaishnavi | Kruthana | 2025-03-16
ST012 | Two-Factor Authentication | REQ-212 | Verify 2FA during login process | User enabled 2FA | 1. Login with 2FA 2. Enter code | Valid 2FA code | User authenticated successfully | 2FA working fine | Pass | High |  | Vaishnavi | Kruthana | 2025-03-16
ST013 | Profile Update | REQ-213 | Verify user can update profile info and save | User logged in | 1. Update profile 2. Save changes | New profile data | Profile updated successfully | Profile updated correctly | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-16
ST014 | Payment Refund Process | REQ-214 | Verify payment refund process works end-to-end | Payment exists and refundable | 1. Initiate refund 2. Confirm refund | Transaction ID | Refund processed and visible in UI | Refund successful | Pass | High |  | Vaishnavi | Kruthana | 2025-03-16
ST015 | Block and Unblock Account | REQ-215 | Verify blocking and unblocking account works | User logged in | 1. Block account 2. Unblock account | Account ID | Account status updates correctly | Block and unblock successful | Pass | High |  | Vaishnavi | Kruthana | 2025-03-16
ST016 | Linked Bank Account Management | REQ-216 | Verify adding and deleting linked bank accounts | User logged in | 1. Add bank account 2. Delete bank account | Bank account data | Bank account added and deleted | Bank account management successful | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-16
ST017 | Payment Status Updates | REQ-217 | Verify payment status updates correctly across app | Payment initiated | 1. Make payment 2. Check status | Payment ID | Status updated correctly | Payment status updated | Pass | High |  | Vaishnavi | Kruthana | 2025-03-16
ST018 | Notification Read Status | REQ-218 | Verify marking notifications read updates UI and DB | User logged in with notifications | 1. Mark notification read 2. Check status | Notification ID | Notification marked read | Notification read status updated | Pass | Low |  | Vaishnavi | Kruthana | 2025-03-16
ST019 | Login Error Handling | REQ-219 | Verify invalid login credentials show error | App deployed | 1. Enter invalid credentials 2. Click login | Invalid username/password | Error message displayed | Error message displayed | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-16
ST020 | Password Complexity Check | REQ-220 | Verify password meets complexity requirements | User registering or resetting password | 1. Enter weak password 2. Attempt save | Weak password | Password rejected with error | Password validation working | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-16
ST021 | Forgot Password Email Content | REQ-221 | Verify content of forgot password email | User requests reset | 1. Request reset 2. Receive email | Registered email | Email content correct and professional | Email content verified | Pass | Low |  | Vaishnavi | Kruthana | 2025-03-16
ST022 | Session Renewal on Activity | REQ-222 | Verify session renewal happens on user activity | User logged in | 1. Perform actions 2. Check session expiry | None | Session expiry extended on activity | Session renewal working | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-16
ST023 | Data Validation on Forms | REQ-223 | Verify all user input forms validate data correctly | App deployed | 1. Enter invalid data 2. Submit forms | Invalid data | Validation errors displayed | Validation working correctly | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-16
ST024 | Application Performance | REQ-224 | Verify application loads pages within acceptable time | App deployed | 1. Load main pages 2. Measure response time | None | Pages load within 2 seconds | Performance acceptable | Pass | Medium |  | Vaishnavi | Kruthana | 2025-03-16
ST025 | Data Backup and Restore | REQ-225 | Verify data backup and restore processes | Backup system configured | 1. Trigger backup 2. Restore data | Backup data | Data restored correctly | Backup and restore successful | Pass | High |  | Vaishnavi | Kruthana | 2025-03-16